## Sheet1
ID | Risk Description | Likelihood (1-5) | Impact (1-5) | Risk Rating | Prevention | Action
1 | Loss of Internet | 2 | 2 | 4 | Keep recent local copy. Regularly commit changes. | Try mobile data. Work on branch of local copy of code.
2 | GCP going down | 1 | 5 | 6 | Keep local copy | Contact Google. Move to local copy
3 | Major Health Issues | 1 | 5 | 6 | Follow safety guidelines | Seek medical attention. Notify team-members / QA Contact
4 | Minor Health Issues | 2 | 3 | 5 | Stock up on Lemsip | Notify team-members, take frequent breaks.
5 | Personal / Social Emergency | 1 | 3 | 4 | Plan for small-term disruption, i.e. agree who could take on a task from you. | Notify team-members, delegate tasks if required.
6 | Poor code organization / Readability Issues | 3 | 1 | 4 | Follow syntax convention, use suitable variable names, comment often. | Create a branch to re-organize code.
7 | Data-loss | 2 | 4 | 6 | Make regular commits / pushes. Backup artifacts and code. | Revert to most recent commit, or pull from.
8 | Disorganised Database | 4 | 5 | 9 | Follow guidelines. Sanitize input. Back-up where necessary. | Create branch to amend code. Revert to recent back-up if required.
9 | Poor Organization / Time Management | 3 | 3 | 6 | Use story-points and prioritization in planning. | Re-organize, plan what can be done in time remaining. Communicate with client to assess.